## Instructions
Using the estimation tracker
At the end of each week, update the status of all activities completed during the week.
Fill in hours spent on each activity during the current week.
If 5 team members each spent an hour, that counts as 5 hours.
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks.
If you are going to have more than one person contribute to a task include their hours too - even if it is a meeting.
During the planning phases, identify the activities to be done during each week.
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
Even if you find that you were WAY off in your estimations, record them anyway.
Gaining experience with estimation will help you manage your time and the project in the long run.
Your instructor will not penalize you for it, this is part of learning to be a software developer.
When making time estimates in the beginning, do not work under the false assumption that everything will always work correctly the first time. People often underestimate the time necessary to complete tasks.
For new activities, identify the type of activity (you can define new types)
Identify people responsible for each activity
Estimate the hours needed for the activity
After each release, look at the "reports" section to see charts of how much time has been spent so far, and what activities it has been spent on.
Use the charts and data to identify needs for improvement.
Acknowledgement
This spreadsheet has been adapted from https://www.se.rit.edu/~sal/SEmanual/Part1.html

## Activities
Activity Short Name | Type | Week | GitHub issue | Responsible | Deadline | Estimated Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage | [10 empty] | Automatically updated
Week 1
2 Interviews | Preparation |  |  | ShaNiece Twitty | Sun | 1 |  | Planned
2 Interviews | Preparation |  |  | Taylor Davis | Sun | 2 |  | Done
2 Interviews | Preparation |  |  | John Zeledon | Sun | 1 |  | Done
1 Interview | Preparation |  |  | Noelia Canela | Sun | 0.5 |  | Done
1 Interview | Preparation |  |  | Brandon Tavares | Sun | 0.5 |  | Planned
1 Interview | Preparation |  |  | Kieran McKinney | Sun | 0.5 |  | Planned
Write Inception Document | Documentation |  |  | Taylor Davis | Sun |  |  | Ongoing
Reviewing Minutes and Inception | Documentation |  |  | Brandon Tavares | Sun |  |  | Ongoing
Issue Tracker
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8

## SummaryData
Note: All data on this sheet updated automatically
Week Label | Week | Total Activities | Estimated Hours | Actual Hours | Total absolute estimation error | Average estimation error %
Week1 | 1 | 0 | 0 | 0 | 0 | #DIV/0!
Week2 | 2 | 0 | 0 | 0 | 0 | #DIV/0!
Week3 | 3 | 0 | 0 | 0 | 0 | #DIV/0!
Week4 | 4 | 0 | 0 | 0 | 0 | #DIV/0!
Week5 | 5 | 0 | 0 | 0 | 0 | #DIV/0!
Week6 | 6 | 0 | 0 | 0 | 0 | #DIV/0!
Week7 | 7 | 0 | 0 | 0 | 0 | #DIV/0!
Week8 | 8 | 0 | 0 | 0 | 0 | #DIV/0!
Week9 | 9 | 0 | 0 | 0 | 0 | #DIV/0!
Week10 | 10 | 0 | 0 | 0 | 0 | #DIV/0!
Week11 | 11 | 0 | 0 | 0 | 0 | #DIV/0!
Week12 | 12 | 0 | 0 | 0 | 0 | #DIV/0!
Week13 | 13 | 0 | 0 | 0 | 0 | #DIV/0!
TOTAL |  |  |  | 0
Activity |  | Total Activities | Actual Effort | % Effort | Average estimation error %
Requirements |  | 0 | 0 | #DIV/0! | #DIV/0!
Design |  | 0 | 0 | #DIV/0! | #DIV/0!
Development |  | 0 | 0 | #DIV/0! | #DIV/0!
Testing |  | 0 | 0 | #DIV/0! | #DIV/0!
Interfaces |  | 0 | 0 | #DIV/0! | #DIV/0!
Documentation |  | 2 | 0 | #DIV/0! | #DIV/0!
Coordination |  | 0 | 0 | #DIV/0! | #DIV/0!
Preparation |  | 6 | 0 | #DIV/0! | #DIV/0!
Delivery |  | 0 | 0 | #DIV/0! | #DIV/0!
TOTAL |  | 8 | 0 | #DIV/0!
Criteria
| Week | Week | Week | Week | Week | Week | Week | Week | Week | Week
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10